Ducor Chemical

Source: Project Management Case Studies

Herold Kerzner, Ph.D.

In the fall of 2000, Ducor Chemical received a research and development contract from one of their most important clients. The client had awarded Ducor with a twelve-month, sole source contract for the R&D effort to create a new chemical that the client required for one of its future products. If Ducor could develop the product, the long-term production contract that would follow could generate significant profits over the next several years.

In addition to various lab personnel who would be used as needed, the contract mandated a senior chemist be assigned for the duration of the project. In the past, the senior chemists had been used mainly for internal rather than external customer projects. This would be the first time a senior chemist had been assigned to this client. With only four senior chemists on staff, the project manager expected the resource negotiation process with the lab manager to be an easy undertaking.

PM:

I understand you´ve already looked over the technical requirements, so you should understand the necessity for assigning you best senior scientist.

Lab manager:

All of my senior scientists are good. Any one of them can do the job. Based upon the timing of you project, I have decided to assign John Thornton.

PM:

Just my luck! You assigned the only one I cannot work with effectively. I have had the misfortune of working with him before. He´s extremely arrogant and unpleasant to work with.

LM:

Perhaps so, but he got the job done, didn´t he?

PM:

Yes, he did. Technically, he is capable. However, his arrogant attitude and sarcasm produced a demoralizing atmosphere for my team. That project was about 3 months in length. This project is at least a year. Also, if follow-on work is generated, as I expect it to be, I´ll be stuck with him for a long time. That´s unacceptable to me. –

LM:

I´ll talk to John and see if I can´t a gag in his mouth. Anyway, you´re a good project manager and you should knot how to work with these technical and scientific Prima Donnas.

PM:

I´ll never be able to maintain my sanity having to work with him full-time for at lest one year. Surely, you can assign on of the other three senior chemists instead.

LM:

Because of the nature of the other projects I have, John is the only senior chemist I can release for one full year. If your project was two or three months, then I might be able to give you one of the other senior chemists.

PM:

I feel like you are dumping Thornton on me without considering what is in the best interest of the Project. Perhaps we should have the sponsor resole this conflict.

LM:

First of all, this is not a conflict. Second, threatening me with sponsor intervention will not help your case. Do you plan on asking for my resources or support ever again in the future? I´m like an elephant. I have a long memory. Third, my responsibility is to meet your deliverable in a manner that is in the best interest of the company.

Try to look at resource assignments through my eyes. You´re worried about the best interest of your project. I have to support some twenty projects and must make decisions in the best interest of the entire company. Benefiting one project at the expense of several other projects is not a good company decision. And all I am paid to make sound company decisions, whereas you are paid to make a Project decision.

PM:

My salary, promotion and future opportunities rest solely on the success of this one project, not twenty.

LM:

Our relationship must be a partnership based upon trust if project management is to succeed. You must trust me when I tell you that your deliverables will be accomplished within time, cost and quality. It´s my job to make that promise and to see that it is kept.

PM:

But what about morale? That should also be a factor. There is also another important consideration. The customer wants monthly team meetings at our location, to access progress.

LM:

I know that, I read the requirements document. Why are the monthly meetings a problem?

PM:

I have worked with this customer before. At the team meetings, they want to hear the technical status from the people doing the work rather than from the project manager. That means that John Thornton would be directly interfacing with the customer at least once a month. Thornton is a “loose cannon” and there is no telling what words will come out of his mouth. If it were not for the interface meetings, I might be agreeable to accept Thornton. But based upon previous experience, he simply does not know when to shut up! He could case irrevocable damage to our project!

LM:
I will take care of John Thornton. And to appease you, I will also attend each on of the customer interface meetings to keep Thornton in line. As far as I´m concerned, Thornton will be assigned and the subject is definitely closed!

THE PROJECT CONTINUED…

John Thornton was assigned to the project team. During the second interface meeting, Thornton stoop up and complained to the customer that some of the tests that the customer requested were worthless, serving no viable purpose. Furthermore, Thornton asserted that if he were left alone, he could develop a product far superior to what the customer had requested.

The customer was furious over Thornton´s remarks ad asserted that they would now evaluate the project performance to date, as well as Ducorś commitment to the project. After the evaluation they would consider whether the project should be terminated, or perhaps assigned to one of Ducor´s competitors. The lab manager had not been present during either of the first two customer interface meetings.

QUESTIONS:

- How do we create a partnership between the project manager and line managers when project manager focuses only on the best interest of his/her project and the line manager is expected to make impartial company decisions?

- Who should have more of a say during negotiations for resources: the project manager or the line manager?

- How should irresolvable conflicts over staffing between the project and line managers be handled?

- Should an external customer have a say in project staffing?

- How do we remove an employee who is not performing as expected?

- Should project managers negotiate for people or deliverables?